## Sheet1
Project X Systems Engineering Scope | SE Oversight | SE Lead | IT Services | RM Engineer: | SME | Engineer X | Engineer Y | Misc | ODCs | Assumptions
1) Develop SE Plan | 80
2) Requirements Management
a) SE Tool Implementation | [9 empty] | Use of Innoslate. This estimate assumes all other engineering tools are already available at no cost to the project
i) Procure Tool | 8 |  | 8 |  |  |  |  | 12 | 4500 | 2 Named license. Some Free Reviewer Licenses. LANL already has Oracle license or SQL Server license available for use. LANL already has a server available for use.
ii) Install Tool |  |  | 24 |  |  |  |  | 12
b) Train Team Members to Use Tool | 24 | 24 |  | 24 | 24 |  |  |  | 25000 | These ODCs are not confirmed
c) Develop Specialized Reports |  |  |  | 80
d) RM Process
i) Deliverable: RM Plan | 80
ii) Deliverable: RM Guide | 80
iii) Deliverable: Document Hierarchy | 12
e) Requirements Capture and Traceability |  |  |  | 1200 | [5 empty] | RM Engineer needed full time for project duration
f) Capture Requirement Sources and Other Artifacts in the Database
g) Establish Traceability Links
h) Maintain Information
i) Generate Reports and Metrics
3) Configuration Management
a) CM Process
i) Deliverable: CM Plan | [5 empty] | 120 |  |  |  | Engineer X is highly experienced in CM
b) Control Change to Requirements and Design | [5 empty] | 312 |  |  |  | Assumes 2 major changes
i) Conduct Impact Analysis
ii) Develop and Approve Change Documentation
iii) Implement Approved Changes
4) Initial Requirements Baseline Development
a) Identify Applicable Regulations |  | 20 |  |  | 10 | 10
b) Develop Operational Requirements Document, if needed |  |  | 20 |  |  | 120 |  |  |  | Assumes help from Operations, who is primarily responsible for this document. SE role is to guide development and ensure clear requirements.
i) Deliverable: ORD
c) Identify documents | 8 | 40 |  |  |  | 40
i) Deliverable: IRB List
d) Clarify Requirements | 20 | 120 |  |  | 40 | 80
e) Establish Measures of Effectiveness |  | 20 |  |  | 10 | 20
f) Develop Discipline-Specific Design Criteria | [5 empty] | 160 |  |  |  | Assume producing Design Criteria for two disciplines
g) Develop Code of Record | [9 empty] | Assume RM Engineer can develop this. Covered in their RM hours
h) Determine Verification & Validation Requirements |  | 120 |  |  | 120
5) Conceptual Baseline Development
a) Systems Analysis | 80 | 80 |  |  | 80 | 120 |  |  |  | These hours include the deliverables
i) Deliverable: Functional Analysis (sufficient to support system specification used for acquisition)
ii) Deliverable: Calculations?
iii) Deliverable: Other analyses?
b) System Architecture Development | 20 | 120 |  |  | 80 | 80
i) Deliverable: Trade Study?
ii) Deliverable: System Asset Hierarchy (sufficient to support system specification used for acquisition)
iii) Deliverable: System Internal Block Diagram(s)
c) Interface Management | 12 | 80 |  |  | 40 | 40
i) Deliverable: Context Diagram
ii) Deliverable: External Interface Matrix (System-level interfaces, I/O exchanges, constraints, existing ICDs)
d) Safety Impact Analysis |  | 10 |  |  | 20 |  | 20 |  |  | Assumes little impact to PFHA, CSPS and DSAs
i) PFHA Impact Analysis
ii) Safety Impact Analysis
e) Specialty Analysis | [7 empty] | 20
i) Seismic (Categories, Accelerations, II/I)
f) System-Level Verification and Validation | 4 | 80 |  |  | 20
g) Technical Risk Management |  | 80
h) Develop Conceptual Design Package |  | 120 |  |  | 120 | 60 | 60 |  |  | Includes the system spec
i) Develop System Specification, including KPPs
6) Support Acquisition Package Development
a) Develop Selection Criteria for Award | 4 | 20 |  |  | 10 |  | 120
i) Deliverable: Selection Criteria for Award
b) Develop Design Agency Statement of Work (Technical Analysis and Products, Quality Program, SE Scope, Logistics/ Supportability, Reviews) |  | 20 |  |  | 20 |  | 160
i) Deliverable: Statement of Work
ii) Deliverable: List of Deliverables
iii) Deliverable: Deliverable format & content requirements
c) Develop Instructions to the Offeror |  | 10 |  |  |  |  | 80
i) Deliverable: Engineering portion of Instructions to the Offeror
d) Develop Design Agency Verification and Validation Requirements |  | 20 |  |  |  |  | 80
i) Design Verification
ii) Component-Level Verification
iii) System-level Verification
iv) Final Product Validation
7) Technical Reviews of Project
a) Conceptual Design Review | 80 | 120 |  |  | 120 | 120 | 120
b) CD-1 Support | 80 | 160 |  |  | 160 | 160 | 160
8) Post-CD1 Support | [9 empty] | Assumes 22 weeks in FY 18 to support procurement, oversight and reviews
a) Design Agency Oversight | 40 | 220 |  |  | 220 | 80 | 80
b) Conduct Technical reviews of Design Agency-Developed Baselines | 40 | 120 |  |  | 120 | 120 | 120 |  |  | Assumes 1 Design Review in FY18 for Design Agent
Hours Subtotals | 672 | 1604 | 52 | 1304 | 1214 | 1642 | 1000 | 44 | 7532
ODC Total | [8 empty] | 29500
| 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
FTE during CD | 0.49333 | 1.0533 | 0.043333 | 1.0867 | 0.72833 | 1.2017 | 0.66667 | 0.036667
FTE Post CD1 | 0.090909 | 0.38636 | 0 | 0 | 0.38636 | 0.22727 | 0.22727 | 0